## WBS Details
|  | Work Breakdown Structure | [8 empty] | cust test
Project Name | cust test(Sub cust 2)_Mixed_07 |  |  |  | Project ID |  | P052 |  | WBS Date | 2026-09-28
Customer / Partner | cust test |  |  |  | End Customer / Sub-Venture |  | Sub cust 2 |  | WBS ID | IN-2026-27-C183-P052
Brief Details | SOW Details |  |  |  | SPOC Details
| Department | Red Team & Adversary Simulation, Cloud Security |  |  | Name |  | Aman / Sahil
| Total Activities | 2 |  |  | Contact No |  | 7854125489 / 7854122547
| UAT/Production env. | mumbai |  |  | Email ID |  | aman@gmail.com / sahilad77@gmail.com
Service Description | [10 empty] | Duration
Service ID | Service Name | Service Quantity | Resource Level | Service Description | Service Frequency | Service Location | Service Model | Project Type | Tools | File Format | Start Date | End Date | Tentative Total Days
WBS-01 | Full Spectrum Red Team Exercise | 1 | L2 | — | Yearly | Onsite — mumbai | NA | Long Term | Cobalt Strike, Metasploit, Mimikatz | Excel | 2026-09-28 | 2027-09-28 | 262
WBS-02 | AWS Security Assessment | 2 | L1=1, Senior=1 | — | Half yearly | Offsite | NA | Long Term | Scout2, CloudMapper, AWS Inspector | PDF | 2026-09-28 | 2027-03-26 | 260
Total | [12 empty] | 522
Special Note:- | Note come from project onboarding process…

## Accounts Details
Accounts Details
Project / Billing Information
Project Name | cust test(Sub cust 2)_Mixed_07 |  | Project ID | P052 |  |  | WBS ID | IN-2026-27-C183-P052
Customer / Partner | cust test |  | Sub-Venture | Sub cust 2 |  |  | Currency | INR
Billing Model | Quarterly Arrears |  | Payment Terms | End of Each Quarter |  |  | PO Status | PO Pending
PO Number | — |  | PO Date | — |  |  | Target Date | —
Invoice Scheduling
Service Name | Milestone / Period | Invoice Target Date | Unit Price | Qty | Currency | Invoice Amount | Invoice Status | Invoice Number | Payment Status | Date of Payment Received
Full Spectrum Red Team Exercise | Quarter 1 | 2026-09-15 | 120000 | 1 | INR | 30000 | Not Raised | — | Not Received | —
Full Spectrum Red Team Exercise | Quarter 2 | 2026-09-23 | 120000 | 1 | INR | 30000 | Not Raised | — | Not Received | —
Full Spectrum Red Team Exercise | Quarter 3 | 2026-09-24 | 120000 | 1 | INR | 30000 | Not Raised | — | Not Received | —
Full Spectrum Red Team Exercise | Quarter 4 | 2026-09-16 | 120000 | 1 | INR | 30000 | Not Raised | — | Not Received | —
AWS Security Assessment | Quarter 1 | 2026-09-22 | 55000 | 2 | INR | 55000 | Not Raised | — | Not Received | —
AWS Security Assessment | Quarter 2 | 2026-09-24 | 55000 | 2 | INR | 55000 | Not Raised | — | Not Received | —
Total Invoice Value | [5 empty] | 230000
Comments / Notes
Note section