## PMS-Screen Status
Steps | Project Flow | Actionable | Status | Date
1 | PMS Module (Process Discussion) | Project Allocation (also Resource & Task Allocation) | Done | 2026-05-05
|  | Project Monitoring (Updates & governance) | Done
|  | Project Closure (touch points with dependencies) | Done
|  | Role description with KRA | Done
|  | Other Department's dependencies understanding | Done
|  | Keka - Limitations | Done
2 | PH Team (Pre-requisite Sharing) | PMS (Step-by-Step) Process description | Done | 2026-05-06
|  | PMS (step-by-step) Keka module screen shots | Done
|  | PMS (Manual tracker) sample for resource & project | Done
|  | Role based mapped responsibilities | Done
|  | Keka - sample templates | Done
| Functional Dept. (Pre-requisite Sharing) | HR Department (Resources master tracker) | Done | 2026-05-11
|  | Sales Department (Client master tracker, Service master tracker, Billing Model, etc.) | Pending
|  | Accounts Department (PO master tracker, Invoice Master tracker, etc.) | Done | 2026-05-18
3 | Screen/Page Designing (Phase - 1) | Team members login | Done | 7-May 8-May
|  | Team Leader login | Done
|  | Project Manager login | Done
|  | HR login | Done | 2026-05-11
|  | Sales login | Done | 2026-05-12
|  | Accounts login | Done
|  | Engagement manager login | Done | 2026-05-13
|  | PMO Login | Done
|  | HOD & BO Login | WIP
4 | Screen/Page Design Review & Modifications (Phase - 2) | Defined all Page Sequence : (Dashboard, Action Center, Projects, Reports, Customers, Resources) | Done | 2026-05-19
|  | All Pages synchronization (from 2 developing logins) | Done | 2026-05-19
|  | All pages reviewed & planning further modifications | Done | 2026-05-19
|  | All pages final review, locking & architecture review | Line-up | 2026-05-22
5 | Development (Phase - 3) | Dashboard & Reports Generation (pending discussion) | Pending | 2026-05-22
|  | Internal Chats (pending discussion) | Pending
|  | Project health & alerts (pending discussion) | Pending
6 | Development (Phase - 4) | Final Management Approval for all the pages (changes & add Ons) | Scheduled | 2026-05-25
|  | Rules implementation (Terms & Conditions) | Scheduled | 26 & 27 May
All Module synchronization
7 | Development (Phase - 5) | Functional testing | Scheduled
Security testing
|  | UAT Testing with dummy data & team | Scheduled
|  | Production Testing (with selective teams) | Scheduled
|  | Feedback gathering & fixing | Scheduled

## PMS-Development-Timeline
Tool Modules | Features Development | Required Timeline (Front end & Back end Included) | Team Count | Days | Tentative Dates
Pre-requisite Documentation | 1. PMS Tool Requirement gathering document 2. Architecture Diagram design 3. Database schema document | 10 Days | 2 | 5 | 08-Jun to 19-Jun | Sahil Lad Kisna Chandarana
HR Dept Basic-Module Development | 1. Employee Onboarding data uploading 2. Employee Offboarding data updation 3. Employee leave data synchronization 4. Client wise leave data synchronization | 08 Days | 2 | 4 | 22-Jun to 25-Jun
A/C Dept. Module Development | 1. Provide approval to sales team by checking PO status & mentioning remarks (in Comments) 2. Raising Invoices based on the billing module by getting automated notification (Additional Comments box) 3. Payment Status updating (Received/Pending/Line-up) | 06 Days | 2 | 3 | 26-Jun 29-Jun 30-Jun
Sales Dept. Module Development | 1. Client Onboarding 2. Raising Invoices based on the billing module by getting automated notification (Additional Comments box) 3. WBS/Project Creation | 10 Days | 3 | 3 | 1-Jul to 3-Jul
Delivery Dept. Module Development | 1. Time-sheet Updation 2. Task Updation 3. Self profile Updation 4. Issue/Query Raising 5. Approval provide on the time-sheets (Leaders only) 6. Team Allocation/Team Leader Allocation (Leaders only) 7. Task Allocation (Leaders only) 8. Reaction (Feedback on task & resource project specific) (Leaders only) 9. WBS acknowledgement, WBS assign to Pm and Sr. pm, pre-requisite collection/validation (all services/activities with their status), Project Status updation (PMO only) 10. Overall governance (Sr. PM, Client EM, PMO & HOD only) + Role wise access control with all above features (Team member, Team Leader, Project Manager, Client EM, PMO, HOD) | 42 Days | 3 | 14 | 6-Jul to 23-Jul
BO Module Development | Full access | 02 Days | 2 | 1 | 2026-07-24
Admin Module Development | Control Panel | 05 Days | 2 | 2 | 27-Jul to 28-Jul
Total Duration | Total Days | 83 Days | 16 | 32
| Total Weeks | 16 Weeks | Weeks | 6
| Total Months | 4 Months | Month | 1.1
Tool Testing-Phases | Functional testing & Report discussion with corrections - (Interns team/Squad-1 team) | Scheduled | 29-Jul - to - 31-Jul
Security testing & Report discussion with Patching - (Vasant Patil)
| UAT Testing with dummy data & dummy team - (Rujuta & Pradeep) | Scheduled | 03-Aug - to - 06-Aug
| Feedback gathering & error fixing - (Dhanashree - Development team) | Scheduled | 10-Aug - to - 13-Aug
| Production Testing (with selective teams) - (Pradeep & Viraj's team) | Scheduled | 17-Aug - to - 20-Aug
| Feedback gathering & Final gap fixing - (Dhanashree - Development team) | Scheduled | 24-Aug - to - 27-Aug
Tool Development | 1] Data preparation & Validation | Scheduled | WIP
| 2] Sample check for old data | Scheduled
| 3] Bulk uploading (Dept. wise) | Scheduled | 24-Aug - to - 27-Aug

## PMS-Tool-Flow-Chart
Codes | Operational Dept (HOD, PMO, EM, Sales, A/C, HR) | Delivery Dept (Sr. PM, PM, TL) |  |  |  | TK - Org
¦
|  |  | ¦ |  |  | \¦/ |  |  | ¦
|  |  | HR Dept. |  |  | Sales Dept. |  |  | Accounts Dept.
|  |  | ¦ |  |  | ¦ |  |  | ¦
|  |  | Employee Directory (EMP ID) |  |  | ¦ ¦ |  |  | Work-Order Directory (PO ID)
|  |  | ¦ |  |  | ¦ |  |  | ¦
|  |  | ¦ ¦ |  |  | Client Directory (Client ID) | <<<----- | Sharing (PO ID) | <<<< ¦
|  |  | ¦ |  |  | \¦/
EM linked
¦
|  |  | ¦ ¦ |  |  | Sharing WBS to PMO Team (WBS ID) |  |  |  | <<<---- | ___ ¦
|  |  | ¦ |  |  | ¦ |  |  |  |  | ¦
|  |  | ¦>>> | Sharing (EMP ID) | ----->>> | PMO Dept. |  |  |  |  | WBS returned to sales dept.
[6 empty] | ¦ |  |  |  |  | ¦
\¦/
|  |  |  | Old Client ¦ (Show Old PM & Sr.PM Name) | <<<----- | Client Profile | ----->>> | New Client
|  |  |  | ¦ |  |  |  | ¦
|  |  |  | \¦/ |  |  |  | \¦/
|  |  |  | PM & Sr. PM l (Show their Bucket count) l (Request an approval to HOD) |  |  |  | PM & Sr. PM l (Show their Bucket count) l (Request an approval to HOD)
|  |  |  | ¦ |  |  |  | ¦
|  |  |  | HOD Approval (on the same PM & Sr.PM name / suggested by himself) |  |  |  | HOD Approval (on the same PM name / suggested by himself)
|  |  |  | ¦ |  |  |  | ¦
PM & Sr.PM Acknowledgement
¦
Pre-requisite Requested By PMO
¦
Pre-requisite Collected By PMO
\¦/
Project is Ready to start (Notify to HOD, Sr.PM, & PM)
/¦\
Actual Project start date marked
\¦/
PM/EM can assign project team as per the project types : 1. Fixed Task Based (one-task-at a time only) 2. MSSP Task Based (Shared task)
EM to assign resources under PM as per the filled Pre-requisites and WBS received from client.
¦
PM (Delivery Dept) Initiate the Assessments as per pre-requisites received (Technical SLA starts @ stage)
¦
PM can allocate resources in specific project