## Phase 1
Phase - 1
Module | Task | Story | Start Date | Target Date | Actual End date
Repository | Database Design | Story 1 — Repository, Database Design for Document Management Description: • Implement the required database design for the Repository module. • Create necessary database tables and relationships for repository/document information. • Include database support for document view logs. • Ensure the database structure supports document upload and management. • Incorporate changes and suggestions discussed during the 24 August review meeting. Acceptance Criteria: • Required Repository database tables and relationships are created. • Repository/document details can be stored successfully. • Required document-management fields are available. • Database supports document view-log information. • Database design is reviewed and finalized. • Changes suggested during the 24 August meeting are incorporated.
Repository | Document Upload & View Logs | Story 2 — Repository, Document Upload & View Log Management Description: • Implement document upload functionality in the Repository module. • Allow users to upload and store required documents. • Store document metadata and related information in the database. • Implement document view logging to track access to repository documents. • Ensure uploaded documents can be accessed based on user permissions. Acceptance Criteria: • Users can upload supported documents successfully. • Uploaded documents are associated with the correct repository information. • Document metadata is stored correctly. • A view log is generated when a document is accessed/viewed. • View logs capture required user, document, and timestamp information. • Users can access documents only according to configured permissions. • Upload and view-log functionality works correctly with the Repository database.
Login Page | Microsoft Authentication | Story 3 — Login Page, Microsoft Authentication Integration Description: • Implement Microsoft authentication on the Login Page. • Integrate the Login Page with Microsoft O365 authentication. • Implement required backend changes for authentication. • Implement required database changes for authentication-related information. • Handle successful and unsuccessful authentication scenarios. • Redirect authenticated users to the appropriate application module. Acceptance Criteria: • Users can log in using configured Microsoft authentication. • Microsoft authentication data is securely handled. • Required authentication information is stored correctly in the database. • Successfully authenticated users are granted application access. • Authentication failures are handled appropriately. • Unauthorized users cannot access protected modules. • Microsoft O365 app registration/configuration is completed. • Login functionality works across supported scenarios.